## Sheet1
Phase | Module | What you prepare | Main scripts/files | Dependency | Status
0 | Architecture Foundation | Project skeleton, configuration, conventions | settings.py, database.py, main.py | None | WIP
1 | SQL Server | DB connection + base ORM | database.py, models | Phase 0
2 | Database Schema | Tables + relationships + seed | models, SQL scripts | Phase 1
3 | Authentication | Register/Login/JWT/Roles | auth router/service/repository | Phase 2 | Skip
4 | Product Catalog | Categories/products/search/filter | product router/service/repository | Phase 2
5 | Inventory | Stock/reservation/availability | inventory service/repository | Phase 4
6 | Cart | Add/remove/update/cart calculation | cart router/service/repository | Phase 4/5
7 | Checkout & Orders | Order creation + pricing | order service/repository | Phase 6
8 | Razorpay | Sandbox order/payment/verification | payment service/router | Phase 7
9 | Payment Failure/Retry | Failure + retry state machine | payment service | Phase 8
10 | Order Lifecycle | Tracking/cancellation | order service | Phase 7/8
11 | Refund | Eligibility/refund/status | refund service/router | Phase 8/10
12 | AI Foundation | LangGraph state/tools | agents/tools | Phase 4–11
13 | Shopping Agent | Product discovery/recommendation | shopping agent/tools | AI Foundation
14 | Order Agent | Cart/order actions | order agent/tools | AI Foundation
15 | Payment Agent | Controlled payment actions | payment agent/tools | Payment
16 | Support Agent | Order/payment/support queries | support agent/tools | Orders
17 | Refund Agent | Refund workflow + HITL | refund agent/tools | Refund
18 | Supervisor | Agent routing/orchestration | supervisor agent | All agents
19 | AI Assistant UI | Chat interface | React AI components | Supervisor
20 | RAG | Policies/FAQ retrieval | knowledge service | Support
21 | Admin | Dashboard/management | admin React + APIs | All core modules
22 | Monitoring | Agent/tool/audit logs | logging/audit services | AI + core
23 | Testing | Unit/integration/E2E | tests/ | All
24 | Docker/README | Deployment/documentation | Docker + README | Final

## GitHub Backlog
Issue ID | Phase | Priority | Module | Type | User Story | Task | Dependency | Acceptance Criteria | Status
SP-001 | M01 | P0 | Foundation | Infrastructure | As a developer, I need project structure | Create React/FastAPI/DB folders | - | Repository structure created | Backlog
DB-001 | M01 | P0 | SQL Server | Database | As a developer, I need SQL database | Create ShopPilotAI DB | SP-001 | DB created successfully | Backlog
DB-002 | M01 | P0 | SQL Server | Database | As a developer, I need commerce tables | Create Users/Product/Cart/Order tables | DB-001 | All tables created | Backlog
SP-010 | M02 | P0 | Product | Backend | As a customer, I need to browse products | Create Product API | DB-002 | Product APIs working | Backlog
SP-020 | M03 | P0 | Cart | Backend | As a customer, I need to manage cart | Create Cart APIs | SP-010 | Add/update/remove works | Backlog
SP-023 | M03 | P0 | Order | Backend | As a customer, I need to place order | Create Order service | SP-020 | Order persisted in SQL Server | Backlog
SP-030 | M04 | P0 | Razorpay | Payment | As a customer, I need to pay | Configure Razorpay Sandbox | SP-023 | Razorpay order generated | Backlog
SP-031 | M04 | P0 | Razorpay | Payment | As a customer, I need payment checkout | Integrate Razorpay Checkout | SP-030 | Checkout opens successfully | Backlog
SP-032 | M04 | P0 | Razorpay | Backend | As system, I need payment verification | Verify payment signature | SP-031 | Payment verified and stored | Backlog
SP-040 | M05 | P1 | Agentic AI | AI Agent | As a customer, I need AI assistance | Setup LangGraph | SP-032 | LangGraph running | Backlog
SP-041 | M05 | P1 | Agentic AI | AI Agent | As system, I need intent routing | Build Supervisor Agent | SP-040 | Correct agent selected | Backlog
SP-050 | M06 | P1 | Shopping Agent | AI Agent | As customer, I need product recommendations | Build Shopping Agent | SP-041 | AI retrieves real products | Backlog
SP-060 | M07 | P1 | Order Agent | AI Agent | As customer, I need order assistance | Build Order Agent | SP-050 | Agent can access order flow | Backlog
SP-070 | M08 | P1 | Refund Agent | AI Agent | As customer, I need refund assistance | Build Refund Agent | SP-060 | Refund eligibility checked | Backlog
SP-080 | M09 | P2 | Admin | Frontend | As admin, I need dashboard | Build Admin Dashboard | SP-070 | Dashboard displays data | Backlog
SP-090 | M10 | P2 | Testing | Testing | As developer, I need reliable application | Create automated tests | SP-080 | Core workflows tested | Backlog
SP-100 | M11 | P2 | Authentication | Security | As customer, I need secure login | Implement JWT | SP-090 | Login works | Backlog
SP-101 | M11 | P2 | RBAC | Security | As admin, I need permissions | Implement RBAC | SP-100 | Customer/Admin permissions work | Backlog
SP-110 | M12 | P2 | Deployment | Infrastructure | As developer, I need deployable app | Dockerize application | SP-101 | Application runs in containers | Backlog

## SQL Server Setup log
SQL ID | Priority | SQL Module | Task | Tables / Objects | Depends On | Status
DB-001 | P0 | Database | Create database | ShopPilotAI | - | Todo
DB-002 | P0 | Core | Create Users | users | DB-001 | Todo
DB-003 | P0 | Core | Create Addresses | addresses | DB-002 | Todo
DB-004 | P0 | Catalog | Create Categories | categories | DB-001 | Todo
DB-005 | P0 | Catalog | Create Products | products | DB-004 | Todo
DB-006 | P0 | Inventory | Create Inventory | inventory | DB-005 | Todo
DB-007 | P0 | Commerce | Create Cart | carts | DB-002 | Todo
DB-008 | P0 | Commerce | Create Cart Items | cart_items | DB-007, DB-005 | Todo
DB-009 | P0 | Commerce | Create Orders | orders | DB-002, DB-003 | Todo
DB-010 | P0 | Commerce | Create Order Items | order_items | DB-009, DB-005 | Todo
DB-011 | P0 | Payment | Create Payments | payments | DB-009 | Todo
DB-012 | P1 | Refund | Create Refunds | refunds | DB-011, DB-009 | Todo
DB-013 | P1 | AI | Agent Execution Logs | agent_execution_logs | DB-002 | Todo
DB-014 | P1 | AI | Agent Tool Calls | agent_tool_calls | DB-013 | Todo
DB-015 | P1 | AI | Customer Interactions | customer_interactions | DB-002 | Todo
DB-016 | P1 | AI | AI Recommendations | ai_recommendations | DB-002, DB-005 | Todo
DB-017 | P1 | Audit | Audit Logs | audit_logs | DB-002 | Todo
DB-018 | P0 | Performance | Create indexes | Products, Orders, Payments, Agents | All relevant tables | Todo
DB-019 | P0 | Data | Seed categories | Categories | DB-004 | Todo
DB-020 | P0 | Data | Seed products | Products | DB-005 | Todo
DB-021 | P0 | Data | Seed inventory | Inventory | DB-006 | Todo
DB-022 | P1 | Data | Seed demo users | Customer/Admin | DB-002 | Todo

## Phase-wise View
Phase | GitHub Milestone | Priority | Main Objective | Completion Criteria
1 | M01 Foundation & DB | 🔴 P0 | React + FastAPI + SQL Server | App connects to SQL Server using Windows Auth
2 | M02 Authentication | 🔴 P0 | Login/Register/JWT | Customer/Admin login works
3 | M03 Products & Inventory | 🔴 P0 | Product catalog + stock | Products and inventory work end-to-end
4 | M04 Cart & Orders | 🔴 P0 | Shopping and order workflow | Cart → Checkout → Order works
5 | M05 Razorpay Sandbox | 🔴 P0 | Payment integration | Order → Razorpay → Verification works
6 | M06 Agentic Foundation | 🟠 P1 | LangGraph + Supervisor | User request routed to correct agent
7 | M07 AI Shopping | 🟠 P1 | AI product discovery | AI searches real DB products
8 | M08 AI Order & Support | 🟠 P1 | AI order/support | AI can answer real order questions
9 | M09 Refund Agent | 🟠 P1 | Cancellation + refunds | AI → eligibility → approval → refund
10 | M10 Admin | 🟡 P2 | Admin operations | Admin can manage commerce
11 | M11 Testing | 🟡 P2 | Quality + security | Core flows tested
12 | M12 Deployment | 🟡 P2 | Docker + docs | New developer can run project